## Read me
Exchange Online Protection Kit: Top 5
Version | 1.0 (2026-10-28; facts re-read on Microsoft Learn 2026-10-28; validated: quality gate, read-only guard, syntax check, Excel recalc)
What this is | The same backlog as the Jira CSV, as a project plan for teams without Jira. One row per control on 'Project plan'; 'Dashboard' shows progress.
Your cells | Yellow cells on 'Project plan': Owner, Start, Due, Status, Done date, Notes. Everything else is filled in or calculated.
Status values | To do, In progress, Blocked, Done, Not applicable. Pick from the drop-down.
% complete | Done = 100%. In progress = 50% (assumption: a simple midpoint, so the dashboard moves before a control is finished). Everything else = 0%. 'Not applicable' rows are left out of the totals.
Effort (h) | Hands-on hours from the guide: upper end of a range, minutes converted to hours. Waiting time (DNS, rollout weeks, recurring reviews) is not included.
Overdue | Due date before today and status not Done or Not applicable.
Example row | Owner: j.doe · Start: 03/11/2026 · Due: 07/11/2026 · Status: In progress · Done date: (empty until Done) · Notes: Report-only since 03/11, review on 06/11.
Details per control | Why, steps, read-only check, verify, licence and sources are in the guide (.md) that ships in the same zip.
Disclaimer | Not affiliated with or endorsed by Microsoft. Test every change in Report-only or on a pilot group first.

## Dashboard
Exchange Online Protection Kit: Top 5 — progress
All figures are formulas over 'Project plan'. 'Not applicable' rows are excluded from % complete.
By area
Area | Controls | Done | In progress | Blocked | Not applicable | % complete | Overdue | Hours left
Preset policies and baseline
Email authentication (SPF, DKIM, DMARC)
Outbound mail and forwarding
Total
By sprint
Sprint | Controls | Done | In progress | Blocked | Not applicable | % complete | Overdue | Hours left
Sprint 1 - Baseline
Sprint 2 - Authenticate your domains
Total

## Project plan
ID | Control | Area | Sprint | Priority | Effort (guide) | Effort (h) | Licence | Owner | Start | Due | Status | Done date | % complete | Overdue | Verify (done when…) | Notes
EX01 | Turn on the Standard preset security policy for all users (Strict for priority accounts) | Preset policies and baseline | Sprint 1 - Baseline | Highest | 2 h | 2 | EOP parts: any Exchange Online plan. Safe Links, Safe Attachments and impersonation in the presets: Defender for Office 365 Plan 1 or 2 (Business Premium, E5 or add-on). |  |  |  | To do |  |  |  | Standard preset rule State is Enabled and covers all accepted domains; Strict covers the priority group; Configuration analyzer shows no policy weaker than Standard for those users.
EX02 | Block automatic forwarding to external addresses and review the forwards that already exist | Outbound mail and forwarding | Sprint 1 - Baseline | Highest | 2 h | 2 | Any Exchange Online plan (EOP). |  |  |  | To do |  |  |  | The Default outbound policy shows AutoForwardingMode Off; every remaining forward is in a named custom policy with an owner; a test inbox rule forwarding outside the tenant returns 5.7.520.
EX03 | Publish SPF and turn on DKIM signing for every domain that sends mail | Email authentication (SPF, DKIM, DMARC) | Sprint 2 - Authenticate your domains | Highest | 3 h | 3 | Any Exchange Online plan. DNS changes at your registrar or DNS host. |  |  |  | To do |  |  |  | Every custom sending domain has exactly one SPF record ending in -all and DKIM Enabled True with Status Valid; a test message shows spf=pass and dkim=pass with header.d=<your domain> in Authentication-Results.
EX04 | Publish DMARC for every domain and move it from p=none to p=reject | Email authentication (SPF, DKIM, DMARC) | Sprint 2 - Authenticate your domains | High | 1 h set-up + 4 to 8 weeks monitoring | 1 | Any plan. DNS changes only. |  |  |  | To do |  |  |  | Every accepted domain returns a DMARC record; sending domains are at p=reject (or on a dated plan to get there); parked domains and onmicrosoft.com are at p=reject; aggregate reports arrive daily.
EX05 | Anti-malware: common attachments filter on with Reject, zero-hour auto purge on, admin-only quarantine | Preset policies and baseline | Sprint 1 - Baseline | High | 30 min | 0.5 | Any Exchange Online plan (EOP). |  |  |  | To do |  |  |  | Every anti-malware policy shows EnableFileFilter True, FileTypeAction Reject, ZapEnabled True and QuarantineTag AdminOnlyAccessPolicy.
Formulas:
Overdue = IF(AND(ISNUMBER([Due]),[Due]<TODAY(),[Status]<>"Done",[Status]<>"Not applicable"),"Yes","")